## Sheet1
Project # | Date Assigned | Project Name | Present Status | Next Step | Expected Completion Date | Comments | Done
2023-9 | Feb 2022 | Drainage project Paving for 143 lane clubhouse-Process # C2024108490 | Engineering plans approved by County | Start mobilization | June 2025
2023-10 | Feb 2022 | Drainage project for clubhouse - Process # C2024108235 | Engineering plans being reviewed | Start mobilization | June 2025
2023-11 | Nov 2022 | 125 Ave gate (roundabout) | Engineering plans being reviewed | Awaiting Permit | To be determined | Awaiting Permit
2024-16 | Aug 2024 | Drainage project 136 Terr & 118 Passage | Design in process |  |  | Will not be scheduled until the 3 above projects are completed
2025-1 | Budgeted Annually | Strom Drain cleaning | Budgeted Annually |  | Feb 2025 | Completed | x
2025-2 | 1/1/2024 | Sidewalk pressure cleaning entrance, signs and pool area | Budgeted |  | Dec 2025 |  | x
2025-3 | 1/1/2024 | Stock mosquito fish | Budgeted |  | April 2025 | Completed | x
2025-4 | Budgeted Annually | Mow lawns, front and back areas, and lake banks | Budgeted |  | 2 times a month (Jan - May & Sept- Dec) 3 times a month June-Aug | Ongoing
2025-5 | Budgeted Annually | Apply Fertilizer and pesticide | Budgeted |  | Every 2 months starting in Jan | Ongoing
2025-6 | Budgeted Annually | Clean lake banks of coconuts and other debris | Budgeted |  | Dec 2025
2025-7 | Budgeted Annually | Clean back areas of debris | Yearly |  | Mowing every 2 weeks Debris pickup once 1 year on Sept. |  | x
2025-8 | Budgeted Annually | Tree trimming before hurricane season |  | Board Approved | May 2025
2025-9 | Budgeted Annually | Annual flower/mulch |  |  | October 2025
2025-10 | Budgeted Annually | Landscape Improvements | To be scheduled | Board Approved | June 2025
2025-11 | Jan 2026 | Painting the curb and center lines | 143 lane ONLY | Board Approved | June 2025
2025-12 | Budgeted Annually | Holiday Community Lights |  | Board Approved | Nov 2025
2025-13 | Feb 2025 | Replace fire panel |  | Board Approved | May 2025
2025-14 | April 2025 | Schedule FPL to clear the field behind SW 124 Ave Rd (mailboxes) |  |  | Completed | Completed | X
2025-15 | April 2025 | Develop group email process to save printing costs | Consult with tech expert | Legal Review | Summer 2025
2025-16 | April 2025 | Review roof option | Referred to subcommitte ACC & Board |  | Winter 2025
2025-17 | April 2025 | Community entrance signs- Pressure clean and painted |  | Board Approved | May 2025 | Completed | 2025-05-07
2025-18 | April 2025 | 2 Metal signs added in Spanish to the 122 Ave and 125 Ave | In process | Board Approved | May 2025 | Completed | 2025-05-20