## Sheet1
Project # | Date Assigned | Project Name | Present Status | Next Step | Expected Completion Date | Comments | Done
2023-11 | Nov 2022 | 125 Ave gate (roundabout) | Work in progress |  | Summer 2026
2024-16 | Aug 2024 | Drainage project 136 Terr & 118 Passage | Awaiting contractor scheduling |  | Summer/ Fall 2026 | Will not be scheduled until the 3 above projects are completed
2026-1 | Budgeted Annually | Storm Drain cleaning | Budgeted Annually |  | Feb 2026 | Completed | x
2026-2 | 1/1/2024 | Sidewalk pressure cleaning entrance, signs and pool area | Budgeted |  | Dec 2026
2026-3 | 1/1/2024 | Stock mosquito fish | Budgeted |  | April 2026 | Completed | x
2026-4 | Budgeted Annually | Mow lawns, front and back areas, and lake banks | Budgeted |  | 2 times a month (Jan - May & Sept- Dec) 3 times a month June-Aug | Ongoing
2026-5 | Budgeted Annually | Apply Fertilizer and pesticide | Budgeted |  | Every 2 months starting in Jan | Ongoing
2026-6 | Budgeted Annually | Clean lake banks of coconuts and other debris | Budgeted |  | Ongoing | Ongoing
2026-7 | Budgeted Annually | Clean back areas of debris | Yearly |  | Mowing every 2 weeks Debris pickup once 1 year on Sept. |  | x
2026-8 | Budgeted Annually | Tree trimming before hurricane season |  | Board Approved | August 2026 | Completed | X
2026-9 | Budgeted Annually | Annual flower/mulch |  |  | October 2026
2026-10 | Budgeted Annually | Landscape Improvements | To be scheduled |  | November 2026
2026-11 | Jan 2026 | Painting the curb and traffic markings | 143 lane ONLY | Board Approved | Summer 2026 | Shortly after paving is completed
2026-12 | Budgeted Annually | Holiday Community Lights |  | Board Approved | Nov 2026
2026-13 | July 2025 | Main gate - repair |  | Permit Approved | Summer / Fall 2026 | Coordinate with roundabout project
2026-14 | Nov 2025 | Pool Leak | Pool Closed - tracking leak | Review by Board | March 2026 | Completed | X
2026-15 | Jan 2026 | Mailbox incident SW 124 Ave Rd | Claim filed / mailboxes ordered |  | Feb 2026 | Completed | X
2026-16 | Feb 2026 | Tennis Courts Nets | Installed |  | Feb 2026 | Completed | X
2026-17 | Nov 2025 | Coordinate colors across roof types | Review by legal | Mailout to residents | Summer 2026 | Completed | X
2026-18 | April 2026 | Repair pool pumps |  |  | May 2026 | Completed | X
2026-19 | Feb 2026 | Gate and clubhouse access equipment | Cost information being gathered | Awaiting completion main gate | Summer/ Fall 2026
2026-20 | May, 2026 | Sw 144 ST and SW 125 Ave gate was damaged by resident | Repaired |  | June , 2026 | Completed | X
2026-21 | July, 2026 | Pressure clean all 3 community entrance signs |  | Board Approved | August, 2026 | Completed | X